NONPROFIT COMMUNICATIONS PLAN

2026 – 2027

Month-by-Month Calendar  ·  2–3 Person Team  ·  Low-Cost Tools

COLOR KEY

| Website | Social | Email | Media | Donors | Volunteers | Grants | Partners |
| --- | --- | --- | --- | --- | --- | --- | --- |

MONTHLY CONTENT FORMULA

1 Website impact story  +  1 volunteer story  +  1 partner feature  +  1 email newsletter  +  8–12 social posts  +  1 media pitch  +  1 grant/sponsor activity  +  1 outcome graphic

= Sustainable communications cadence with minimal staff and budget

| JULY 2026 · COMMUNITY STORIES | Stories are the most powerful delivery tool for information. Gather 2-3 real client stories and let their voices carry your mission. |
| --- | --- |

| WEEK | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 Jul 1-5 | Mon 1 Website: Publish client success story | Tue 2 Social: Launch storytelling campaign | Wed 3 | Thu 4 Social: Post #2 — quote from client | Fri 5 |
| Week 2 Jul 7-11 | Mon 7 Email: Monthly newsletter — community impact | Tue 8 | Wed 9 Volunteers: Collect 2-3 story submissions | Thu 10 | Fri 11 Social: Volunteer spotlight post |
| Week 3 Jul 14-18 | Mon 14 Media: Pitch human-interest story | Tue 15 | Wed 16 Social: Outcome data graphic post | Thu 17 | Fri 18 Partners: Partner feature — draft copy |
| Week 4 Jul 21-25 | Mon 21 Grants: Research Q3 grant opportunities | Tue 22 | Wed 23 Website: Publish partner feature story | Thu 24 | Fri 25 Social: Month recap post + metrics |
| MONTHLY KPIs Sponsors: Target — 2 outreach emails ¦ Success — 1 meeting booked Content: Target — 5 pieces published ¦ Success — All on schedule Form Fills: Target — 10 inquiries ¦ Success — 5 completions |  |  |  |  |  |

| AUGUST 2026 · BACK-TO-SCHOOL / COMMUNITY SUPPORT | Community need spikes in August — align your messaging with urgency. Target school supply sponsors and engage families who need services most. |
| --- | --- |

| WEEK | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 Aug 4-8 | Mon 4 Website: Update seasonal services page | Tue 5 Social: Community resources post #1 | Wed 6 | Thu 7 Social: Community resources post #2 | Fri 8 |
| Week 2 Aug 11-15 | Mon 11 Email: Back-to-school program newsletter | Tue 12 | Wed 13 Partners: Outreach to 3 school/retail sponsors | Thu 14 | Fri 15 Social: Sponsor highlight post |
| Week 3 Aug 18-22 | Mon 18 Volunteers: Publish volunteer spotlight story | Tue 19 | Wed 20 Media: Pitch back-to-school community story | Thu 21 | Fri 22 Social: Behind-the-scenes program photos |
| Week 4 Aug 25-29 | Mon 25 Grants: Submit open grant applications | Tue 26 | Wed 27 Social: Program photos post #2 | Thu 28 | Fri 29 Website: Month-end blog post |
| MONTHLY KPIs Sponsors: Target — 3 sponsor outreach emails ¦ Success — 1 sponsor confirmed $500+ Content: Target — 5 pieces published ¦ Success — 1 media pickup Form Fills: Target — Families register for fall ¦ Success — 8 completions |  |  |  |  |  |

| SEPTEMBER 2026 · DONORS & SPONSORS | Q4 fundraising season starts NOW. Warm up your donors in September. Steward existing donors, cultivate new ones, lock in sponsor commitments. |
| --- | --- |

| WEEK | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 Sep 2-5 | Tue 2 Website: Update donor recognition page | Wed 3 Social: Sponsor appreciation post #1 | Thu 4 | Fri 5 Social: Sponsor appreciation post #2 |  |
| Week 2 Sep 8-12 | Mon 8 Email: Newsletter: impact of giving | Tue 9 | Wed 10 Donors: Personal thank-you to top 10 donors | Thu 11 | Fri 12 Social: Outcome graphic: $ raised → lives |
| Week 3 Sep 15-19 | Mon 15 Media: Pitch community investment story | Tue 16 | Wed 17 Donors: Begin annual report outline | Thu 18 | Fri 19 Social: Impact data graphic post |
| Week 4 Sep 22-26 | Mon 22 Grants: Research fall grant deadlines | Tue 23 Donors: 3 donor stewardship calls | Wed 24 | Thu 25 Website: Publish impact story | Fri 26 |
| MONTHLY KPIs Sponsors: Target — 2 confirmed Q4 sponsors ¦ Success — Combined value $2,000+ Content: Target — 5 pieces + open rate ≥25% ¦ Success — Email open rate hit Form Fills: Target — Donor pledge form live ¦ Success — 6 completions |  |  |  |  |  |

| OCTOBER 2026 · ANNUAL REPORT & IMPACT | Your annual report is your most powerful credibility tool. Publish your annual report and let outcomes speak — donors, grantors and sponsors are watching. |
| --- | --- |

| WEEK | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 Oct 6-10 | Mon 6 Website: Launch annual report (Canva Flipbook) | Tue 7 | Wed 8 Social: Outcome highlights — 1 stat per post | Thu 9 | Fri 10 Social: Outcome post #2 |
| Week 2 Oct 13-17 | Mon 13 Email: Annual report release email — full send | Tue 14 | Wed 15 Social: Key stats as data graphics (3 posts) | Thu 16 | Fri 17 Donors: Begin year-end cultivation calls |
| Week 3 Oct 20-24 | Mon 20 Media: Pitch impact results story | Tue 21 | Wed 22 Website: Film + publish Q4 quarterly video | Thu 23 | Fri 24 Social: Video share post |
| Week 4 Oct 27-31 | Mon 27 Grants: Submit fall grant applications | Tue 28 | Wed 29 Donors: Year-end donor cultivation outreach | Thu 30 | Fri 31 Social: Halloween / community post |
| MONTHLY KPIs Sponsors: Target — Logos in annual report ¦ Success — 2 sponsors renew for year-end Content: Target — Annual report + 6 deliverables ¦ Success — Open rate ≥28% Form Fills: Target — Report download form ¦ Success — 10 completions |  |  |  |  |  |

| NOVEMBER 2026 · GIVING & GRATITUDE | Giving Tuesday is your Super Bowl. Plan by Oct 31, schedule in advance. Your biggest fundraising opportunity. Send 2 donation appeals. Make every message feel personal. |
| --- | --- |

| WEEK | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 Nov 3-7 | Mon 3 Website: Launch year-end giving campaign page | Tue 4 | Wed 5 Donors: Donor story series — post #1 | Thu 6 | Fri 7 Social: Donor story post #2 |
| Week 2 Nov 10-14 | Mon 10 Email: Giving Tuesday campaign email | Tue 11 Social: Giving Tuesday social blitz (schedule 3) | Wed 12 | Thu 13 Donors: Donation appeal email #1 | Fri 14 |
| Week 3 Nov 17-21 | Mon 17 Media: Pitch community needs — holiday angle | Tue 18 | Wed 19 Volunteers: Volunteer recognition posts (2) | Thu 20 | Fri 21 Social: Gratitude countdown post |
| Week 4 Dec 1 | Mon Dec 1 Donors: Donation appeal email #2 — Giving Tuesday follow-up Grants: Research Q1 2027 grant calendar |  |  |  |  |
| MONTHLY KPIs Sponsors: Target — 1 Giving Tuesday match sponsor ¦ Success — Match announced; boosts gifts Content: Target — Campaign page + 2 emails + 10 social ¦ Success — Campaign live by Nov 1 Form Fills: Target — Donation/pledge form on landing page ¦ Success — 15 completions |  |  |  |  |  |

| DECEMBER 2026 · YEAR-END IMPACT | Your donors, volunteers, and partners gave their all — make them feel like heroes. Close with gratitude. A warm year-end message builds loyalty for 2027. |
| --- | --- |

| WEEK | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 Dec 1-5 | Mon 1 Website: Publish year-in-review story | Tue 2 | Wed 3 Social: Top 5 accomplishments series — post 1 | Thu 4 | Fri 5 Social: Top accomplishments post 2 |
| Week 2 Dec 8-12 | Mon 8 Donors: Donor recognition posts + thank-you email | Tue 9 | Wed 10 Email: Year-end donation appeal email | Thu 11 | Fri 12 Social: Year in numbers data graphic |
| Week 3 Dec 15-19 | Mon 15 Media: Final pitch — year-end results story | Tue 16 | Wed 17 Partners: Partner appreciation outreach emails | Thu 18 | Fri 19 Social: Partner shout-out post |
| Week 4 Dec 22-31 | Mon 22 Email: Annual thank-you campaign email | Tue 23 | Wed 24 Volunteers: Team + volunteer year-end celebration | Thu 25 | Fri 26 Social: Happy New Year post (schedule) |
| MONTHLY KPIs Sponsors: Target — 2 sponsors signed for Jan 2027 ¦ Success — Agreements before Dec 31 Content: Target — Year-in-review + 5 deliverables ¦ Success — Thank-you open rate ≥30% Form Fills: Target — 2027 interest sign-up form ¦ Success — 8 completions |  |  |  |  |  |

| JANUARY 2027 · VISION & GOALS | January sets the tone for everything — publish your goals publicly. A fresh year is your best recruiting pitch to volunteers, donors, and sponsors. |
| --- | --- |

| WEEK | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 Jan 5-9 | Mon 5 Website: Publish 2027 annual goals webpage | Tue 6 | Wed 7 Social: New year vision series — mission post #1 | Thu 8 | Fri 9 Social: Vision post #2 |
| Week 2 Jan 12-16 | Mon 12 Email: Annual outlook newsletter | Tue 13 | Wed 14 Donors: Thank year-end donors — call or note | Thu 15 | Fri 16 Social: Vision post #3 |
| Week 3 Jan 19-23 | Mon 19 Volunteers: Launch spring volunteer recruitment | Tue 20 | Wed 21 Partners: Schedule Q1 stakeholder meetings | Thu 22 | Fri 23 Social: Volunteer recruitment post |
| Week 4 Jan 26-30 | Mon 26 Grants: Research + calendar Q1 grant opps | Tue 27 | Wed 28 Media: Outreach — share 2027 org priorities | Thu 29 | Fri 30 Social: Month wrap-up + goals post |
| MONTHLY KPIs Sponsors: Target — 5 targets ID'd; 3 intro emails sent ¦ Success — 1 meeting booked Content: Target — 4 pieces by Jan 31 ¦ Success — All published on time Form Fills: Target — Volunteer + sponsor inquiry forms live ¦ Success — 5 completions |  |  |  |  |  |

| FEBRUARY 2027 · COMMUNITY IMPACT | Impact data is your best content — one compelling stat can win a grant. Pull Q4 2026 outcomes and turn them into shareable graphics and donor stories. |
| --- | --- |

| WEEK | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 Feb 2-6 | Mon 2 Website: Publish Q4/annual impact story | Tue 3 | Wed 4 Social: Client success campaign — post #1 | Thu 5 | Fri 6 Social: Client success post #2 |
| Week 2 Feb 9-13 | Mon 9 Email: Program spotlight newsletter — outcomes | Tue 10 | Wed 11 Donors: Personalized impact email to top donors | Thu 12 | Fri 13 Social: Valentine's — community love post |
| Week 3 Feb 16-20 | Mon 16 Volunteers: Volunteer appreciation posts (2) | Tue 17 | Wed 18 Media: Pitch human-interest story | Thu 19 | Fri 20 Social: Volunteer shout-out post |
| Week 4 Feb 23-27 | Mon 23 Grants: Submit Q1 grant applications | Tue 24 | Wed 25 Social: Outcomes data graphic post | Thu 26 | Fri 27 Website: Month-end impact update |
| MONTHLY KPIs Sponsors: Target — 3 sponsor proposals with impact data ¦ Success — 1 confirmed $1,000+ Content: Target — 5 pieces + 1 grant submitted ¦ Success — All published Form Fills: Target — Impact report / program interest form ¦ Success — 6 completions |  |  |  |  |  |

| MARCH 2027 · PARTNERSHIPS | Partners multiply your reach without multiplying your cost. One well-placed partner spotlight can earn co-marketing, in-kind donations, and joint grants. |
| --- | --- |

| WEEK | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 Mar 2-6 | Mon 2 Website: Publish partner spotlight story | Tue 3 | Wed 4 Social: Community collaboration posts (3) | Thu 5 | Fri 6 Social: Collaboration post #2 |
| Week 2 Mar 9-13 | Mon 9 Email: Partnership-focused newsletter | Tue 10 | Wed 11 Partners: Reach out to 3 spring event sponsors | Thu 12 | Fri 13 Social: Partner spotlight post |
| Week 3 Mar 16-20 | Mon 16 Media: Pitch joint collaboration story | Tue 17 | Wed 18 Donors: Spring event sponsor outreach emails | Thu 19 | Fri 20 Social: Sponsor announcement post |
| Week 4 Mar 23-27 | Mon 23 Grants: Research Q2 grant opportunities | Tue 24 | Wed 25 Website: Film + publish Q1 quarterly video | Thu 26 | Fri 27 Social: Video share + call to action |
| MONTHLY KPIs Sponsors: Target — 2 spring event sponsors by Mar 31 ¦ Success — Combined value $1,500+ Content: Target — 5 pieces + video ≥100 views ¦ Success — All published Form Fills: Target — Spring event RSVP / sponsor form ¦ Success — 8 completions |  |  |  |  |  |

| APRIL 2027 · VOLUNTEER ENGAGEMENT | A volunteer today may be a major donor tomorrow. Treat them like gold. April is National Volunteer Month — best time to recruit, recognize, and retain volunteers all year. |
| --- | --- |

| WEEK | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 Apr 7-11 | Mon 7 Website: Publish volunteer story + open positions | Tue 8 | Wed 9 Volunteers: National Volunteer Month campaign launch | Thu 10 | Fri 11 Social: Volunteer spotlight post #1 |
| Week 2 Apr 14-18 | Mon 14 Email: Volunteer opportunities newsletter | Tue 15 | Wed 16 Volunteers: Open SignUpGenius — share link | Thu 17 | Fri 18 Social: Recruitment post — share sign-up link |
| Week 3 Apr 21-25 | Mon 21 Volunteers: Volunteer recognition posts — 2 individuals | Tue 22 | Wed 23 Media: Pitch volunteer recognition story | Thu 24 | Fri 25 Social: Recognition post #2 |
| Week 4 Apr 28-30 | Mon 28 Grants: Submit Q2 grant applications | Tue 29 Donors: Volunteer-to-donor cultivation email | Wed 30 |  |  |
| MONTHLY KPIs Sponsors: Target — Ask 2 corps to send employee volunteers ¦ Success — 1 corporate day booked Content: Target — 4 pieces + 10 new volunteer sign-ups ¦ Success — Via SignUpGenius Form Fills: Target — Volunteer application form on site ¦ Success — 10 completions |  |  |  |  |  |

| MAY 2027 · ADVOCACY & AWARENESS | Advocacy stories make funders pay attention and elevate grant competitiveness. Show that your org moves the needle on policy and public awareness — that sets you apart. |
| --- | --- |

| WEEK | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 May 5-9 | Mon 5 Website: Update advocacy page with 2027 priorities | Tue 6 | Wed 7 Social: Legislative awareness posts (3) | Thu 8 | Fri 9 Social: Awareness post #2 |
| Week 2 May 12-16 | Mon 12 Email: Action alert newsletter — 1 clear ask | Tue 13 | Wed 14 Partners: Partner co-post on shared advocacy issue | Thu 15 | Fri 16 Social: Partner collaboration post |
| Week 3 May 19-23 | Mon 19 Media: Pitch advocacy success story | Tue 20 | Wed 21 Social: Policy impact outcome graphic | Thu 22 | Fri 23 Social: Advocacy win celebration post |
| Week 4 May 27-30 | Tue 27 Grants: Research summer grant deadlines | Wed 28 Donors: Advocacy donor update email — connect giving to impact | Thu 29 | Fri 30 |  |
| MONTHLY KPIs Sponsors: Target — 1 advocacy-aligned sponsor intro ¦ Success — Intro meeting scheduled Content: Target — 4 pieces + click rate ≥5% ¦ Success — All published Form Fills: Target — Advocacy action form (petition/pledge) ¦ Success — 12 completions |  |  |  |  |  |

| JUNE 2027 · MID-YEAR IMPACT | Your mid-year report proves to funders you are on track. Energize your team, give donors proof you deliver, and set up fall major donor asks. |
| --- | --- |

| WEEK | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 Jun 2-6 | Mon 2 Website: Publish mid-year impact report | Tue 3 | Wed 4 Social: Metrics + outcomes series (3 posts) | Thu 5 | Fri 6 Social: Outcomes post #2 |
| Week 2 Jun 9-13 | Mon 9 Email: Mid-year progress newsletter | Tue 10 | Wed 11 Social: Data graphic posts (2) | Thu 12 | Fri 13 Social: Data graphic post #2 |
| Week 3 Jun 16-20 | Mon 16 Media: Pitch community impact — summer angle | Tue 17 | Wed 18 Website: Film + publish Q2 quarterly video | Thu 19 | Fri 20 Social: Video share post |
| Week 4 Jun 23-27 | Mon 23 Donors: Mid-year major donor cultivation calls | Tue 24 | Wed 25 Grants: Quarterly comms + grant pipeline review | Thu 26 | Fri 27 Social: Half-year celebration post |
| MONTHLY KPIs Sponsors: Target — 2 fall sponsors locked before summer ¦ Success — Signed by Jun 30 Content: Target — Mid-year report + 5 deliverables ¦ Success — Report shared with board Form Fills: Target — Mid-year survey + fall program form ¦ Success — 10 completions |  |  |  |  |  |